## Sheet1
Tuner & Metronome RACI Matrix
2025-03-11
Task | Hajera F. | Rainy W. | Mike G. | Phil M. | SDG Developers Director
Tone Generator, Metronome, Chromatic Tuner, and Settings Backend | I | I | R | A, I | I
User Interface (UI) Design | I | R | C | A, I | I
Localization | R | C | I | A, I | I
Testing | R | R, C | R, C | A, I | I
R: Responsible
A: Accountable
C: Consulted
I: Informed
Note on B4: Role Description: The translator is responsible primarily for writing the localizable strings file by consulting subject matter reference works such as dictionary entries, videos, and encyclopedia articles. She must ensure that she understands the proper context of the words and strings used in the application as well as the right shade of meaning in the translation. After cross checking wordlist entries with multiple sources, she must consult native speakers for those languages that she is not proficient in. A wordlist is expected to be 70-90% accurate before handing in for review by an outside language consultant. The translator also helps with testing the application, checking to see whether localized text strings show up properly in the view and do not exceed control boundaries. She must also ensure that the typography and format of the written text (text direction, capitalization, punctuation) conforms to the locale.
Note on C4: Role Description: The designer is responsible primarily for the frontend look, layout, and user interface design. She must also provide application color ways and icons. She also helps with testing and must stay informed of localization efforts to ensure that localized text strings remain within proper view boundaries.
Note on D4: Role Description: The programmer is responsible primarily for the backend development of features using the Swift programming language and the UIKit framework. Tone generator, metronome, and chromatic tuner audio engines are imported from open-source repositories and adjusted or built upon as needed. He must be consulted by the UI designer and testers, and stay informed of localization efforts in order to ensure proper implementation thereof. He also tests the application to ensure that his implementations are functional and satisfactory.
Note on E4: Role Description: The manager coordinates and is responsible and accountable for all project development efforts, and must stay informed of any issues that might come up and provide guidance as to their resolution. He reports progress to the project stakeholder. The manager also directly assists in the hands-on implementation of backend development, frontend design, and localization.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Considering just putting 'A' for PM tasks rather than all the letters. Thoughts?